## RohanMengade
Prof. Stefan Edlich
|  | Milestones | Rohan Mengade
No | Work/Task | Description | Sub Tasks | Date | Professor Feedback | Percentage Complete
1 | Expose Creation | Preparation of 2 page Expose for Thesis |  | 10th Feb 2021 | Yes | 100%
2 | Research | Research Methodology | Included in Exposee |  | Yes
3 | Research | Extensive research on work, data sets and finding the ways to collect the data for the project work | Research | April 1-April 10 | Yes | 100%
5 | Research | Identified categories of fashion products for which data should be generated | Categorries Identification | April 10-April 17 | Yes | 100%
7 | Research | Started scraping the data, collecting the data | Data Collection | April 17-April 24 | Yes | 100%
8 | Data collection | Data Collection methods Creation of datasets Data preparation | 1.Data Collection (Web Scraping, Scraper tools, Bing, Google, and retail stores websites) [T shirts, Jeans, Tops] 2. Database Creation 3. Connected with company for data formats,type of file and other things for data collection and pre-processing 4. Worked on data generation for T shirts (1000 images, Format PNG, Size: 1024*1024 ) | April 24-April 30 | Yes | 40%
9 | Technology Read | Learn about GANs | 1. Implement basic GAN for Handwritten digits recognition in python. (For better outcomes, need tuning on GPU) 2. Working on Jeans data to scrape (1000 images, Format PNG, Size: 1024*1024 ) 3. Working on GAN implementation for T Shirts (!!!!) | May 1- May 17 | Yes | 100%
10 | Data collection | Creation of datasets Data preparation | Data preparation for Jeans Images data to scrape (1000 images, Format PNG, Size: 1024*1024 ) | May17- May 23 | Yes | 100%
11 | Technology Read | Learn about GANs | Research about various types of GANs and implement one GAN. | May 23-May 31 | Yes | 100%
12 | Data collection | Creation of datasets Data preparation | Identifying and Getting more fashion category data for model (So far I have 3-4 fashion items data ) | May 23-May 31 | Yes | 100%
13 | Technology Read | Learn about GANs | Lesen von GAN-Papier "Visually-Aware Fashion Recommendation and Design with Generative Image Models" | May 23-May 31 | Yes | 100%
14 | Data collection | Creation of datasets Data preparation | Scraping-Daten für Kleidungsstücke | May 23-May 31 | Yes | 100%
15 | Data collection | Creation of datasets Data preparation | Scraping-Daten für Kleidungsstücke | May 23-May 31 | Yes | 100%
16 | Data collection | Sales Performance Data Analysis | 1. Working on real time sales performance data analysis to get fashion insights 2. Language and softwares (Python and PowerBI) | June 1- June 15 | Yes | In Progress
17
18
19
20